## Task breakdown
Assessment criteria | Task | Team Member | Due date | Status
Presentation | Create report template based on A2 | GD | 2019-10-18 | Completed
Team Profile Website | Keep team name? | All | 2019-10-18 | Completed
Coordination | Complete task breakdown spreadsheet | GD | 2019-10-26 | Completed
Project Description | Overview - notes in bullet form for each section | All | 2019-11-03 | Completed - GD, BT, MR
Project Description | Detailed Description - Aims - notes in bullet form for each section | All | 2019-11-03 | Completed - GD, MR
Project Description | Detailed Description - Plans and Progress - notes in bullet form for each section | All | 2019-11-03 | Completed - GD
Project Description | Detailed Description - Roles - notes in bullet form for each section | All | 2019-11-03 | Completed - GD
Project Description | Detailed Description - Scope and Limits - notes in bullet form for each section | All | 2019-11-03 | Completed - GD, BT, MR
Project Description | Detailed Description - Tools and Technologies - notes in bullet form for each section | All | 2019-11-03 | Completed - GD, BT
Project Description | Detailed Description - Testing - notes in bullet form for each section | All | 2019-11-03 | Completed - GD
Project Description | Detailed Description - Timeframe - notes in bullet form for each section | All | 2019-11-03 | Completed - GD, MR, Ben
Project Description | Detailed Description - Risks - notes in bullet form for each section | All | 2019-11-03 | Completed - GD, BT
Project Description | Detailed Description - Group processses and comms - notes in bullet form for each section | All | 2019-11-03 | Completed - GD
Skills and jobs | Notes in bullet form for the section | All | 2019-11-03 | Completed - GD, BT
Group Reflection | Group reflection - Notes in bullet form for the section | All | 2019-11-03 | Completed - GD
Prototype | Put together hardware - arduino, sensors, wifi, relay, display | GD | 2019-11-08 | In Progress
Prototype | Arduino programming | GD | 2019-11-08 | In Progress
Prototype | IoT app (Blynk) | GD | 2019-11-08 | In Progress
Prototype | Design schematics for prototype | GD | 2019-11-09
Team Profile Website | Update personal information if we get new members | Ben | 2019-11-15
Team Profile report section | Update for A3 |  | 2019-11-15
Tools | Take content from A2 and update for A3 report |  | 2019-11-15
Project Description | Overview - take notes in bullet form and turn into final text |  | 2019-11-15
Project Description | Detailed Description - Aims - take notes in bullet form and turn into final text |  | 2019-11-15
Project Description | Detailed Description - Plans and Progress - take notes in bullet form and turn into final text |  | 2019-11-15
Project Description | Detailed Description - Roles - take notes in bullet form and turn into final text |  | 2019-11-15
Project Description | Detailed Description - Scope and Limits - take notes in bullet form and turn into final text |  | 2019-11-15
Project Description | Detailed Description - Tools and Technologies - take notes in bullet form and turn into final text |  | 2019-11-15
Project Description | Detailed Description - Testing - take notes in bullet form and turn into final text |  | 2019-11-15
Project Description | Detailed Description - Timeframe - take notes in bullet form and turn into final text | GD | 2019-11-15
Project Description | Detailed Description - Risks - take notes in bullet form and turn into final text |  | 2019-11-15
Project Description | Detailed Description - Group processses and comms - take notes in bullet form and turn into final text |  | 2019-11-15
Skills and jobs | Take notes in bullet form and turn into final text |  | 2019-11-15
Group Reflection | Individual paragraph | All | 2019-11-15
Group Reflection | Group reflection - Take notes in bullet form and turn into final text |  | 2019-11-15
Presentation | Review whole assignment agaisn the specification to make sure we have covered every question fully and submit | GD | 2019-11-17
Team Profile Website | Add page for Group process and detail changes from A2 | Ben
Team Profile Website | Modify ideal jobs page, taking content from A1 and A2, adding career plans which also need comparing | Ben