## Task breakdown
Assessment criteria | Sequence | Task | Team Member | Due date | Status
Presentation | 1 | Finalise task list | GD |  | Completed
Draft Presentation | 2 | Decide video type and style | All |  | Current idea 26/10/19 - Produce the first introduction video for our DIY retic controller project. Youtube instructiional video style. Overview of the DIY system, what it can do and what parts and software it uses. Use direct to camera presentation with cut aways to static images, other videos or picture in picture (PIP)
Draft Presentation | 3 | Brainstorm video content | All
Draft Presentation | 4 | Create storyboard and script template | GD | 2019-10-26 | Completed
Draft Presentation | 5 | Collate ideas and draft Story Board | All | 2019-11-01 | Completed - GD
Draft Presentation | 6 | Write draft Script based on Story Board | Ben | 2019-11-01 | In Progress
Draft Presentation | 7 | Submit Story board and script drafts |  | 2019-11-03
Final Presentation | 8 | Film video of prototype functioning | GD | 2019-11-08
Final Presentation | 9 | Take photos of protype | GD | 2019-11-08
Final Presentation | 10 | Collect other images, website screen shots etc required for the final presentation
Final Presentation | 11 | Film presenter reading script
Final Presentation | 12 | Edit video - cut aways, PIP
Final Presentation | 13 | Submit video |  | 2019-11-17