## Sheet1
Group Members |  | GD | SS | BT | JF | MR
Assignment Period | Week 1 (WE 20/10/19) | Procure hardware for prototype. Review manuals and instructions for basic configuration of each sensor and the WIFI module, plus the Blynk app. Create Microsoft Teams channel, report template, task list. Populate bullet point ideas in report template and task list. | Switching groups |  | Switching groups | Away
| Week 2 (WE 27/10/19) | Continue to Populate bullet point ideas in report template and task list. Set up WLAN for the project on home network. Configure WIFI module and blynk to connect to Arduino Mega over the internet. | Switching groups | Populate bullet point ideas in report template and task list. Research more about the technologies underpinning the project | Switching groups | Populate bullet point ideas in report template and task list. Research more about the technologies underpinning the project
| Week 3 (WE 3/11/19) | Finish populating bullet point ideas in the report. Connect sensors and get them working one at a time. Study Blynk and Arduino, learn how to add multiple sensors into an Arduino sketch and control via Blynk app |  | Producing instrcutional video draft for A5. Researching how to guides and code examples for features |  | Updating the report sections as per task list. Research more about the technologies underpinning the project
| Week 4 (WE 10/11/19) | Get prototype finalised with multiple sensors feeding back to Blynk, and control a relay from Blynk. Document future features in MS Teams Planner |  | Producing instrcutional video for A5. Researching code examples for some features. Complete report input |  | Updating the report sections as per task list.
| Week 5 (WE 17/11/19) | Complete report input, record demonstration video clips and pictures for use in video presentation and instructions | Complete report input | Producing instrcutional video for A5. Researching code examples for some features. Complete report input | Complete report input | Complete report input
Work Post Assignment - We are supposed to put our names in here rather than use the "venture capitalist question" roles |  | GD | SS | BT | JF | MR
After Assignment due date | Week 6 | Coordinate team. Update project plan. Optimise hardware selection, such that all features can be accommodated using the cheapest and easiest hardware. |  | Code remaining features |  | Work on instructions on how to use the systems vs the technical instructions of how to set it up (how much moisture do plants need, should you water during daylight or night, how long after rain should you wait before watering again, etc, general watering advice).
| Week 7 | Coordinate team. Update project plan. Design hardware enclosure requirements and select off the shelf enclosures for the microcontroller and sensors. | Set up YouTube channel, web page domain name, social media accounts. Ad revenue from YouTube | Code remaining features |  | Work out how we can procure and dispatch the kits most efficiently - sell via eBay but kit is shipped direct from supplier to the buyer, that way we don't have to hold stock etc
| Week 8 | Coordinate team. Update project plan.Procure desired components and enclosures and assemble, working with Marketing & Administration to document the process for YouTube video series and written documentation. | Build web page and determine what to do about SEO (pay for a service or maintain within team). End user forum on webpage. Google ad revenue from webpage. | Optimise prototype code to make sure it is as efficient as possible |  | Work out how we can procure and dispatch the kits most efficiently - sell via eBay but kit is shipped direct from supplier to the buyer, that way we don't have to hold stock etc
| Week 9 | Coordinate team. Update project plan. Procure desired components and enclosures and assemble, working with Marketing & Administration to document the process for YouTube video series and written documentation. | Record YouTube video footage and written documentation images | Optimise prototype code to make sure it is as efficient as possible |  | Develop any branding required, such as logos or packaging
| Week 10 | Coordinate team. Update project plan.Test hardware in the field. | Record YouTube video footage and written documentation images | Optimise prototype code to make sure it is as efficient as possible |  | Provide parts list to potential supplier and negotiate our buy cost
| Week 11 | Coordinate team. Update project plan. | Produce YouTube video series draft | Programme the kit, working with Marketing & Administration to document the process for YouTube video series and written documentation |  | Select a supplier/s, determine what other costs are involved, like eBay fees
| Week 12 | Coordinate team. Update project plan. Review Documentation | Produce written documentation draft | Test software on final hardware in the field |  | Review competition and decide on an end sale price point, taking into account buy cost and any seller fees or other overheads
| Week 13 | Coordinate team. Update project plan. | Finalise YouTube video series. Review Documentation | Review Documentation
| Week 14 | Coordinate team. Update project plan. | Finalise written documentation
| Week 15 | Coordinate team. Update project plan. | Activate SEO, advertise launch on Social media, Publish YouTube series | Set up public GitHub repo and load final code and documentation for the public to access |  | Turn on eBay listing